## Old (hidden)
Project name | TEMPLATE FOR PROJECT TASK LIST FOR DELPHIX MAINFRAME Project
Project manager | Gajalakshmi Sundararajan
Project start date | 2022-03-28
Project finish date | 2022-04-13
Duration | 13 days
% complete | 0%
Exported on | 2022-03-22
Task number | Outline number | Name | Assigned to | Duration | Start | Finish | Depends on | % complete
| 1 | Infrastructure
1 | 1.1 | Linux/VM |  |  | 3/28/2022 | 2022-07-04 |  | 0%
2 | 1.1.1 | VM Teams create/change VMs as per Blueprint | PopupLinux + ClientLinux | 6 days | 3/28/2022 | 2022-04-04 |  | 0%
3 | 1.1.2 | Download OVA for VMware Sphere | PopupLinux + ClientLinux | 2 days | 3/28/2022 | 3/29/2022 |  | 0%
4 | 1.1.3 | Reinstall PopUp on (Source VM) - Run new OVA | PopupLinux + ClientLinux | 1 day | 3/30/2022 | 3/30/2022 | 3 - Download OVA for VMware Sphere | 0%
5 | 1.1.4 | VM Team - Add disk to Delphix Virtualization VM as per blueprint | PopupLinux + ClientLinux | 1 day | 3/28/2022 | 3/28/2022 |  | 0%
6 | 1.1.5 | Delphix appliances - config & performance health check | PopupLinux + ClientLinux | 1 day | 3/29/2022 | 3/29/2022 | 5 - VM Team - Add disk to Delphix Virtualization VM as per blueprint | 0%
7 | 1.1.6 | Delphix appliances - config changes if required based on health check | PopupLinux + ClientLinux | 2 days | 3/30/2022 | 3/31/2022 | 6 - Delphix appliances - config & performance health check | 0%
8 | 1.1.7 | Check Port assignment for Linux VMs (should be same as POC) | PopupLinux + ClientLinux | 1 day | 2022-05-04 | 2022-05-04 | 5 - VM Team - Add disk to Delphix Virtualization VM as per blueprint | 0%
9 | 1.1.8 | Install new Delphix Engine Virtualization | PopupLinux + ClientLinux | 1 day | 3/29/2022 | 3/29/2022 | 5 - VM Team - Add disk to Delphix Virtualization VM as per blueprint | 0%
10 | 1.1.9 | Create an Environment in Delphix | PopupLinux + ClientLinux | 1 day | 2022-06-04 | 2022-06-04 | 8 - Check Port assignment for Linux VMs (should be same as POC) | 0%
11 | 1.1.10 | Check toolkit and EDSI | PopupLinux + ClientLinux | 1 day | 2022-01-04 | 2022-01-04 | 9 - Install new Delphix Engine Virtualization | 0%
12 | 1.1.11 | Configure D-Source | PopupLinux + ClientLinux | 1 day | 2022-07-04 | 2022-07-04 | 11 - Check toolkit Toolkit and EDSI | 0%
13 | 1.1.12 | Setup License Server(Linux) | PopupLinux + ClientLinux | 1 day
14 | 1.2 | Mainframe
15 | 1.2.1 | Install Migration Server | IBM Mainframe System Programmer | 1 day |  |  | - | 100%
16 | 1.2.2 | Set up Transport Volumes (3 x 53Gb) (non-SMS) | ClientMainframe | 1 day |  |  | -
17 | 1.2.3 | Install Corraling Utility | PopupMainframe + IBM Mainframe System Programmer | 1 day |  |  | -
18 | 1.3 | Popup(Mainframe)
19 | 1.3.1 | Userid setup | PopupMainframe | 1 day |  |  | 4
20 | 1.3.2 | Userid Logon Validation | PopupMainframe | 1 day |  |  | 19
21 | 2 | Migration to Popup
22 | 2.1 | Data Migration Setup
23 | 2.1.1 | Install/Customise (De-)Corraling Utility | PopupMainframe | 1 day |  |  | 4
24 | 2.1.2 | Check Firewall and Ports between LPAR and PopUp | IBM Mainframe System Programmer + Network Team and PopupLinux | 1 day | 3/31/2022 | 3/31/2022 | 8 | 100%
25 | 2.1.3 | Check Security on Server Migration Utility | ClientMainframe | 1 day | 3/31/2022 | 3/31/2022 | 15 | 0%
26 | 2.1.4 | Check VOLSER for Migration Server | PopupLinux | 1 day | 3/31/2022 | 3/31/2022 | 4 | 0%
27 | 2.1.5 | Test Corraling utility to add 1+ datasets to transport volume | IBM Mainframe System Programmer+ PopupMainframe | 1 day |  |  | 26
28 | 2.1.6 | Test transfer of volume using Migration Server to zD&T | IBM Mainframe System Programmer+ PopupMainframe | 1 day | 2022-04-04 | 2022-04-04 | 27,24,25 ( 24 - Check Firewall and Ports between LPAR and PopUp, 25 - Check Security on Server Migration Utility | 0%
29 | 2.1.7 | Test De-Corraling to complete transfer of data to Popup | PopupMainframe | 1 day |  |  | 28
30 | 3 | Discover Mainframe Application Subsystems and Data for Gold Copy |  | 8 days | 2022-04-04 | 4/13/2022 |  | 0%
31 | 3.1 | Identify Applications in scope |  |  |  |  | -
32 | 3.1.1 | (For each in scope application):
33 | 3.1.1 | Identify / size all subsystem DB2 objects | IBM DB2 System Programmer and GSL Application DBA +PopUpMainframe | 1 day | 2022-04-04 | 2022-04-04 | 31 | 0%
34 | 3.1.1.1 | …... |  | 0 |  |  | 31
35 | 3.1.2 | Identify / Size all subsystem CICS objects | IBM CICS System Programmer + PopUpMainframe | tbc | 2022-04-04 | 2022-04-04 | 31 | 0%
36 | 3.1.3 | Identify and Size subsystem other objects i.e. files, JCLs, Batch jobs , Procs etc | GSL Application TEAM + PopUpMainframe | 1 day | 2022-04-04 | 2022-04-04 | 31 | 0%
37 | 3.1.4 | Gather, Understand Install and Shakedown instructions | GSL Application TEAM + PopUpMainframe | 2 days | 2022-04-04 | 2022-05-04 | 31 | 0%
38 | 3.1.5 | Liaise with SME's (Application / DB2 / etc ) as required | GSL Application TEAM + PopUpMainframe | 0 |  |  | 31
39 | 3.1.6 | Application Discovery document Complete | GSL Application TEAM | 0 |  |  | 33,34,35,36,37,38
40 | 3.2 | Migrate Application |  |  |  |  | 29
41 | 3.2.1 | (For each in scope application): ie GSL | PopupMainframe
42 | 3.2.1.1 | Application components:
43 | 3.2.1.1.1 | DB2: capture DDL for tables | PopupMainframe | 1 day |  |  | 30
44 | 3.2.1.1.2 | Corral all application objects (not data) | PopupMainframe | tbc |  |  | 30
45 | 3.2.1.1.3 | Transfer Application objects (not data) to Popup | PopupMainframe | tbc |  |  | 43,44
46 | 3.2.1.1.4 | Decorral Application objects | PopupMainframe | tbc |  |  | 45
47 | 3.2.1.1.5 | Build application on Popup | PopupMainframe |  |  |  | 46
48 | 3.2.1.1.5.1 | create tables and other objects on PopUp | PopupMainframe | 2 day |  |  | 50
49 | 3.2.1.1.5.2 | Customise JCL | PopupMainframe | tbc |  |  | 48,50
50 | 3.2.1.1.5.3 | Customise DB2 if required | PopupMainframe | tbc |  |  | 47
51 | 3.2.1.1.6 | Populate with application data: | PopupMainframe
52 | 3.2.1.1.6.1 | Unload of DB2 tables / imagecopies ( Timeline agreed) | PopupMainframe + GSL Application DBA | tbc |  |  | 39
53 | 3.2.1.1.6.2 | Corral required Application objects (DATA) | PopupMainframe | tbc |  |  | 52
54 | 3.2.1.1.6.3 | Transfer Application objects (DATA) to Popup | PopupMainframe | tbc |  |  | 53
55 | 3.2.1.1.6.4 | Decorral Application objects (DATA) | PopupMainframe | tbc |  |  | 54
56 | 3.2.1.1.6.5 | DB2: Load db2 tables | PopupMainframe | tbc |  |  | 55,48
57 | 3.2.1.1.7 | Shake down Application | PopupMainframe |  |  |  | 56,47
58 | 3.2.1.1.7.1 | tbc | PopupMainframe | tbc |  |  | 57
59 | 4 | zD&T virtualisation |  | 4 days | 2022-08-04 | 4/13/2022 |  | 0%
60 | 4.0.1 | Start / Stop Server - Ready for Delphix Ingestion | PopupLinux | 4 days | 2022-05-04 | 2022-08-04 |  | 0%
61 | 4.0.2 | Shake down All subsystems | PopupLinux | 2 days | 2022-07-04 | 2022-08-04 |  | 0%
62 | 4.0.3 | Ingest PopUp and Virtualize the Gold Copy | PopupLinux | 1 day | 2022-11-04 | 2022-11-04 | 4 - Reinstall PopUp on (Source VM) - Run new OVA, 28 - Start / Stop Server - Ready for Delphix Ingestion | 0%
63 | 4.0.4 | Verify Virtual PopUp Subsystem - Log onto CICS application on virtual PopUp | PopupLinux | 1 day | 2022-12-04 | 2022-12-04 |  | 0%
64 | 4.0.5 | Verify Virtual PopUp for All Subsystems | PopupLinux | 2 days | 2022-08-04 | 2022-11-04 |  | 0%
65 | 4.0.6 | Run and test Batch Jobs for Subsystems | PopupLinux | 2 days | 2022-12-04 | 4/13/2022 |  | 0%
66 | 4.0.7 | Document and Handover to Client | PopupLinux | 0 |  |  |  | 0%

## PopupProjectTasklist
Task List for PopUp Virtualization of an Application(s)
Task No | Outline number | Task Name | Estimated Effort (days) | Assigned to | CURRENT STATUS | Location of Document Template | Final version of document, edited for this specific project
1 | 1 | Project Definition & Kickoff
2 | 1.1 | Project Kick off meeting |  | PopUp Manager | NOT STARTED
3 | 1.2 | Project Scope workshop |  | PopUp Manager | NOT STARTED
4 | 1.3 | Create use cases, validation points, test plan |  | PopUp Manager | NOT STARTED | http://docs.popup-mainframe.com/files/A1%20-%20CLIENT%20ProjectName%20-%20Use%20Cases%20%26%20Validation%20Points_V0.01.pptx
5 | 1.4 | Create Project charter |  | PopUp Manager | NOT STARTED
6 | 1.5 | Review the project charter |  | Client | NOT STARTED
7 | 1.6 | Sign off the project charter |  | Client | NOT STARTED
8 |  | MILESTONE Project Definition & Kickoff completed
9 | 2 | Architecture & Application Discovery​
10 | 2.1 | Architecture questionnaire
11 | 2.1.1 | Architecture workshop - discuss/share the current application/scope architecture |  | Client + PopUpMFLead | NOT STARTED | http://docs.popup-mainframe.com/files/A1%20-%20CLIENT%20ProjectName%20-%20PopUp_and_Delphix_Architecture_Questionnaire_V0.01.xlsx
12 | 2.1.2 | Update the Architecture questionnaire |  | Client | NOT STARTED
13 | 2.1.3 | Review of the Architecture questionnaire updates |  | Client + PopUpMFLead | NOT STARTED
14 | 2.1.4 | Sign off of the Architecture questionnaire document |  | Client | NOT STARTED
15 |  | MILESTONE Architecture questionnaire completed
16 | 2.2 | Infrastructure Blueprint
17 | 2.2.1 | Internal Discussion to Create Blueprint as per Clients Architecture Questionnaire |  | PopUpMFLead+PopUpLINUXLead
18 | 2.2.2 | share the Infrastructure Blueprint(VM reqs,memory etc) of Delphix to the Client & Discussion |  | Client + PopUpLINUXLead | NOT STARTED
19 | 2.2.3 | share the Infrastructure Blueprint(VM reqs,memory etc) of Popup to the Client & Discussion |  | Client + PopUpLINUXLead | NOT STARTED
20 | 2.2.4 | Client to Review the Infrastructure Blueprint(s) of Popup & Delphix shared by Popup Team |  | Client | NOT STARTED
21 | 2.2.5 | Sign off/Agreement on the VM specifications/Infrastructure Blueprint |  | Client | NOT STARTED
22 |  | MILESTONE Infrastructure Blueprint completed
23 | 2.3 | Discover Mainframe Application Subsystems and Data for Gold Copy |  |  | NOT STARTED
24 | 2.3.1 | Identify Applications in scope
25 | 2.3.2 | <Application Name> (for each of the application)
26 | 2.3.2.1 | Liaise with SME's (Application / Db2 / etc ) as required |  | Client+PopUpMFLead+PopUpMFDeveloper
27 | 2.3.2.2 | Client to update the Application Discovery document |  | Client |  | http://docs.popup-mainframe.com/files/A2%20-%20CLIENT%20ProjectName%20-%20Application%20Discovery_V0.01.xlsm
28 | 2.3.2.3 | Review of the Application Discovery document |  | PopUpMFLead + PopUpMFDeveloper
29 | 2.3.2.4 | Sign off of the Application Discovery document |  | Client
30 |  | MILESTONE Identify Applications in scope completed
31 |  | MILESTONE Application Discovery document Sign off completed
32 | 2.4 | Formulate Solution ( Create PopUp Architecture Design Document)
33 | 2.4.1 | Formulate Solution
34 | 2.4.1.1 | Create PopUp Architecture Design Document |  | PopUpMFLead+PopUpLINUXLead
35 | 2.4.1.2 | Review/Rework PopUp Architecture Design Document |  | Client + PopUpMFLead+PopUpLINUXLead | NOT STARTED
36 | 2.4.1.3 | Signoff of the PopUp Architecture Design Document (PADD) |  | Client
37 |  | MILESTONE PADD Sign off completed
38 |  | MILESTONE Architecture & Application Discovery completed
39 | 3 | Popup(Mainframe) Infrastructure Setup & Basic Configuration
40 | 3.1 | Share OVA to Client |  | PopUpLINUXLead | NOT STARTED
41 | 3.2 | Download OVA ( ~ 60 GB) |  | Client | NOT STARTED
42 | 3.3 | VM Teams create/change VMs as per Blueprint shared by PopUp Team |  | Client | NOT STARTED
43 | 3.4 | Network / firewall changes (if required ) |  | Client | NOT STARTED
44 |  | MILESTONE Create VM as per Blueprint for Popup Mainframe completed
45 | 3.5 | OVAs Config and Validation |  | PopUpLINUXLead | NOT STARTED
46 | 3.5.1 | OVAs Config & performance health check - Validation |  | PopUpLINUXLead | NOT STARTED
47 | 3.5.2 | OVAs Config changes if required |  | PopUpLINUXLead | NOT STARTED
48 | 3.5.3 | OVAs health check validated |  | PopUpLINUXLead | NOT STARTED
49 |  | MILESTONE OVA Config and Validation completed
50 | 3.6 | Setup POpUP Source,Target and license server |  |  | NOT STARTED
51 | 3.6.1 | Config PopUp license server , Config PopUp Source & Target Server |  | PopUpLINUXLead | NOT STARTED
52 | 3.6.2 | Generate & apply PopUp license key |  | PopUpLINUXLead | NOT STARTED
53 | 3.6.3 | Start z/OS on PopUp Source |  | PopUpLINUXLead | NOT STARTED
54 |  | MILESTONE Setup PopUp Source,Target and license server completed
55 |  | MILESTONE PopUp(Mainframe) Infrastructure Setup & Basic Configuration completed
56 | 4 | Delphix Virtualzation Infrastructure Setup & Basic Configuration |  |  | NOT STARTED
57 | 4.1 | Share OVA to Client |  | PopUpLINUXLead | NOT STARTED
58 | 4.2 | Download OVA |  | Client
59 | 4.3 | VM Teams create/change VMs as per Blueprint shared by PopUp Team |  | Client | NOT STARTED
60 | 4.4 | Network / firewall changes (if required ) |  | Client | NOT STARTED
61 |  | MILESTONE Create VM as per Blueprint for Delphix Virtualization completed
62 | 4.5 | OVAs Config and Validation |  | PopUpLINUXLead
63 | 4.5.1 | OVAs Config & performance health check - Validation |  | PopUpLINUXLead | NOT STARTED
64 | 4.5.2 | OVAs Config changes if required |  | PopUpLINUXLead | NOT STARTED
65 | 4.5.3 | OVAs health check validated |  | PopUpLINUXLead | NOT STARTED
66 |  | MILESTONE OVA Config and Validation completed
67 | 4.6 | Setup Delphix Virtualization Engine
68 | 4.6.1 | Config Delphix Virtualisation Engine |  | PopUpLINUXLead | NOT STARTED
69 | 4.6.2 | Register Delphix Engine (license) |  | PopUpLINUXLead | NOT STARTED
70 |  | MILESTONE Setup Delphix Virtualization Engine completed
71 |  | MILESTONE Delphix Virtualzation Infrastructure Setup & Basic Configuration completed
72 | 5 | Delphix Virtualization Engine Verification
73 | 5.1 | Create an Environment in Delphix Virtualization Engine |  | PopUpLINUXLead | NOT STARTED
74 | 5.2 | Check toolkit and EDSI |  | PopUpLINUXLead | NOT STARTED
75 | 5.3 | Configure D-Source |  | PopUpLINUXLead | NOT STARTED
76 | 5.4 | Data Ingestion |  | PopUpLINUXLead | NOT STARTED
77 |  | MILESTONE Delphix Virtualization Engine Verification Completed
78 | 6 | Mainframe - Install & Setup |  |  | NOT STARTED
79 | 6.1 | Client Mainframe
80 | 6.1.1 | Install Data Migration Server Utility |  | Client
81 | 6.1.2 | Install / Customize Corraling Utility |  | PopUpMFDeveloper
82 |  | MILESTONE Client Mainframe Install & Setup completed
83 | 6.2 | PopUp Mainframe
84 | 6.2.1 | Userid setup |  | PopUpMFDeveloper
85 | 6.2.2 | Userid Logon Validation |  | PopUpMFDeveloper
86 | 6.2.3 | Install / Customize Corraling Utility |  | PopUpMFDeveloper
87 |  | MILESTONE PopUp Mainframe Install & Setup completed
88 |  | MILESTONE Mainframe Install & Setup completed
89 | 7 | Mainframe - Verification & Validation |  |  | NOT STARTED
90 | 7.1 | Client Mainframe
91 | 7.1.1 | Test Corraling utility to add 1+ datasets to transport volume |  | PopUpMFDeveloper
92 | 7.1.2 | Check Security on Migration Server Utility |  | Client
93 | 7.1.3 | Check VOLSER for Migration Server (Transport Volumes) |  | Client
94 | 7.1.4 | Test transfer of volume using Migration Server to zD&T |  | PopUpMFDeveloper
95 |  | MILESTONE Client Mainframe Verification & Validation completed
96 | 7.2 | Popup Mainframe
97 | 7.2.1 | Test De-Corraling to complete the transfer of data to Popup |  | PopUpMFDeveloper
98 |  | MILESTONE Popup Mainframe Verification & Validation
99 |  | MILESTONE Mainframe Verification & Validation completed
100 | 8 | Include following sections where applicable: |  |  | NOT STARTED
101 | 8.1 | Db2
102 | 8.1.1. | Db2 (General)
103 | 8.1.1.1 | Setup
104 | 8.1.1.1.1 | Customize Db2 settings to match client's installation, as close as possible |  | PopUpMFLead
105 | 8.1.1.1.2 | Calculate PopUp DASD requirements and ensure sufficient is available |  | PopUpMFLead
106 | 8.1.1.1.3 | Identify Buffer Pools etc required for PopUp "clone" |  | PopUpMFLead
107 | 8.1.1.1.4 | Corral as required |  | PopUpMFDeveloper
108 | 8.1.1.1.5 | Decorral on Popup if required |  | PopUpMFDeveloper
109 | 8.1.1.1.6 | Configure Db2 on Popup |  | PopUpMFLead
110 | 8.1.1.1.7 | Re-IPL when appropriate |  | PopUpMFDeveloper
111 |  | MILESTONE Db2 General - Setup Completed
112 |  | MILESTONE Db2 General Completed
113 | 8.1.2 | Db2 for <Application>(1 Table with 90,000 rows/records)
114 | 8.1.2.1 | Setup
115 | 8.1.2.1.1 | Identify application specific Tables/Libraries |  | Client
116 |  | MILESTONE Db2 Appl - Setup Completed
117 | 8.1.2.2 | Preparation
118 | 8.1.2.2.1 | Calculate approximate space requirements for Unload files |  | PopUpMFLead
119 | 8.1.2.2.2 | Calculate transfer method DASD requirements and ensure sufficient is available |  | PopUpMFLead
120 | 8.1.2.2.3 | Identify Correct Release of:
121 | 8.1.2.2.3.1 | Execution JCL/PROCLIBs |  | Client
122 | 8.1.2.2.3.2 | EXECutable code |  | Client
123 | 8.1.2.2.3.3 | DBRM's |  | Client
124 |  | MILESTONE Db2 Appl - Release Identification Completed
125 | 8.1.2.2.4 | Identify / Provide DDL for all required tables/tablespaces |  | Client
126 | 8.1.2.2.5 | Create/Modify table unload JCL to suit the PopUp transfer capabilities available ( split where necessary ) |  | PopUpMFDeveloper
127 | 8.1.2.2.6 | Unload data from Source Tables
128 | 8.1.2.2.6.1 | Capture "unload"/syspunch |  | PopUpMFDeveloper
129 | 8.1.2.2.6.2 | Capture row counts (actual rows unloaded) |  | PopUpMFDeveloper
130 |  | MILESTONE Db2 Appl - Unload data Completed
131 | 8.1.2.2.7 | Use CORRALing tool to set up data transfer JCL |  | PopUpMFDeveloper
132 | 8.1.2.2.8 | Create CORRALing scripts for automated execution |  | PopUpMFDeveloper
133 |  | MILESTONE Db2 Appl - Preparation Completed
134 | 8.1.2.3 | Corral Data
135 | 8.1.2.3.1 | Transfer Code Base (Execution JCL/Code/DBRM's etc ) to PopUp |  | PopUpMFDeveloper
136 | 8.1.2.3.2 | Transfer DDL to POPUP |  | PopUpMFDeveloper
137 | 8.1.2.3.3 | Transfer data / unload cards to Popup |  | PopUpMFDeveloper
138 |  | MILESTONE Db2 Appl - Corral Data Completed
139 | 8.1.2.4 | DeCorral (PopUp)
140 | 8.1.2.4.1 | Decorral Application objects |  | PopUpMFDeveloper
141 | 8.1.2.4.2 | Confirm all data transferred successfully (use row counts captured above) |  | PopUpMFDeveloper
142 |  | MILESTONE Db2 Appl - DeCorral Data Completed
143 | 8.1.2.5 | Post-Decorral
144 | 8.1.2.5.1 | Modify JCL to suit PopUp environment |  | PopUpMFDeveloper
145 | 8.1.2.5.2 | Customise DDL / Buffer Pools to match PopUp |  | PopUpMFLead
146 | 8.1.2.5.3 | Create required tables on PopUp |  | PopUpMFDeveloper
147 | 8.1.2.5.4 | Load Db2 tables onto PopUp Sub-system |  | PopUpMFDeveloper
148 | 8.1.2.5.5 | Verify all rows loaded ( vs Actual row counts captured above ) |  | PopUpMFDeveloper
149 | 8.1.2.5.6 | Execute RUNSTATS for required, non-empty tables |  | PopUpMFDeveloper
150 | 8.1.2.5.7 | Bind
151 | 8.1.2.5.7.1 | Programs ( LOAD & DBRM ) |  | PopUpMFDeveloper
152 | 8.1.2.5.7.2 | Package Bind JCL |  | PopUpMFDeveloper
153 | 8.1.2.5.7.3 | Package Bind Cards |  | PopUpMFDeveloper
154 | 8.1.2.5.7.4 | Plan Bind Cards |  | PopUpMFDeveloper
155 | 8.1.2.5.7.5 | Execute Package Binds |  | PopUpMFDeveloper
156 | 8.1.2.5.7.6 | Execute Plan Binds |  | PopUpMFDeveloper
157 |  | MILESTONE Db2 Appl - Bind Completed
158 |  | MILESTONE Db2 Appl - Post Decorral Completed
159 | 8.1.2.6 | Smoke Test
160 | 8.1.2.6.1 | Execute designated application program to confirm operability |  | PopUpMFDeveloper
161 |  | MILESTONE Db2 Appl - Smoke test Completed
162 |  | MILESTONE Db2 Applicatiion Completed (per Application)
163 |  | MILESTONE Db2 Completed (for all Applications)
164 | 8.2 | VSAM estimation for /VSAM file |  |  | NOT STARTED
165 | 8.2.2 | VSAM - <Application>
166 | 8.2.2.2 | Preparation
167 | 8.2.2.2.1 | Depending on transfer method:
168 | 8.2.2.2.1.1 | Identify DELETE/DEFINE Cluster details |  | PopUpMFDeveloper
169 |  | MILESTONE VSAM Appl - Cluster Del/Definition Completed
170 | 8.2.2.2.2 | Identify Correct Release of:
171 | 8.2.2.2.2.1 | Execution JCL/PROCLIBs |  | Client
172 | 8.2.2.2.2.2 | EXECutable code |  | Client
173 |  | MILESTONE VSAM Appl - Release Identification Completed
174 | 8.2.2.2.3 | Use CORRALing tool to set up data transfer JCL |  | PopUpMFDeveloper
175 | 8.2.2.2.4 | Create CORRALing scripts for automated transfer of all Data objects |  | PopUpMFDeveloper
176 |  | MILESTONE VSAM Appl - Preparation Completed
177 | 8.2.2.3 | Corral Data (Mainframe) for each VSAM dataset
178 | 8.2.2.3.2 | CORR(EXPORT) method then
179 | 8.2.2.3.2.1 | EXPORT VSAM to Transport Volume |  | PopUpMFDeveloper
180 |  | MILESTONE VSAM Appl - Corral Data Completed
181 | 8.2.2.4 | DeCorral (PopUp)
182 | 8.2.2.4.1 | Transfer Code Base (Execution JCL/Code/DBRM's etc ) to PopUp |  | PopUpMFDeveloper
183 |  | MILESTONE VSAM Appl - DeCorral Data Completed
184 | 8.2.2.5 | Post-Decorral
185 | 8.2.2.5.1 | Confirm all data transferred successfully |  | PopUpMFDeveloper
186 | 8.2.2.5.2 | Modify JCL to suit PopUp environment |  | PopUpMFDeveloper
187 |  | MILESTONE VSAM Appl - Post DeCorral Completed
188 | 8.2.2.6 | Smoke Test For all VSAM files
189 | 8.2.2.6.1 | Execute designated application program to confirm operability |  | PopUpMFDeveloper
190 |  | MILESTONE VSAM Appl -Smoke Test Completed
191 |  | MILESTONE VSAM Application Completed (per Application)
192 |  | MILESTONE VSAM Completed (for all Applications)
193 | 8.3 | CICS
194 | 8.3.1 | CICS (General)
195 | 8.3.1.1 | Setup
196 | 8.3.1.1.1 | Ensure correct release of CICS is installed |  | PopUpMainframe
197 | 8.3.1.1.2 | Identify CSD file |  | PopUpMainframe
198 | 8.3.1.1.3 | Identify other CICS libraries |  | PopUpMainframe
199 | 8.3.1.1.4 | Corral / FTP as required |  | PopUpMainframe
200 | 8.3.1.1.5 | Decorral on PopUp if required |  | PopUpMainframe
201 | 8.3.1.1.6 | Modify CSD for transactions to test |  | PopUpMainframe
202 | 8.3.1.1.7 | Re-IPL when appropriate |  | PopUpMainframe
203 |  | MILESTONE CICS General - Setup Completed
204 |  | MILESTONE CICS General Completed
205 | 8.3.2 | CICS (Application- {1,2....n} ) For each Application , Repeat the below
206 | 8.3.2.1 | Setup
207 | 8.3.2.1.1 | Identify application specific libraries |  | Application Team
208 |  | MILESTONE CICS Appl - Setup Completed
209 | 8.3.2.2 | Preparation
210 | 8.3.2.2.1 | Agree transfer method(s) ( Migration Utility / FTP / etc ) |  | PopupMainframe&Application Team
211 | 8.3.2.2.2 | Use CORRALing tool to set up data transfer JCL (automation/schedule where necessary) |  | PopupMainframe
212 | 8.3.2.2.3 | Create CORRALing scripts for automated execution |  | PopUpMainframe
213 |  | MILESTONE CICS Appl - Preparation Completed
214 | 8.3.2.3 | Corral Data
215 | 8.3.2.3.1 | Transfer application specific CICS libraries (BMS, etc ) |  | PopUpMainframe
216 |  | MILESTONE CICS Appl - Corral Data Completed
217 | 8.3.2.4 | DeCorral
218 | 8.3.2.4.1 | Restore application libraries |  | PopUpMainframe
219 |  | MILESTONE CICS Appl - DeCorral Data Completed
220 | 8.3.2.5 | Smoke Test
221 | 8.3.2.5.1 | Execute designated application program to confirm operability |  | PopupMainframe&Application Team
222 |  | MILESTONE CICS Appl - Smoke Test Completed
223 |  | MILESTONE CICS Application Completed (per Application)
224 |  | MILESTONE CICS Completed for all of the Applications
225 | 8.4 | IMS
226 | 8.4.1 | IMS (General)
227 | 8.4.1.1 | Setup
228 | 8.4.1.1.1 | Ensure correct release of IMS is installed |  | PopUpMainframe
229 | 8.4.1.1.2 | Identify IMS started tasks (DBCTL or Full IMS DB/DC and whether or not CSL required) |  | PopUpMainframe
230 | 8.4.1.1.3 | Identify required files (RESLIB/SDFSMAC/MODBLKS/DBDLIB/PSBLIB/ACBLIBs) |  | PopUpMainframe
231 | 8.4.1.1.4 | Identify other IMS libraries (RECON etc) |  | PopUpMainframe
232 | 8.4.1.1.5 | Corral / FTP as required |  | PopUpMainframe
233 | 8.4.1.1.6 | Decorral on PopUp if required |  | PopUpMainframe
234 | 8.4.1.1.7 | Update PROCLIB with new libraries |  | PopUpMainframe
235 | 8.4.1.1.8 | Re-IPL when appropriate |  | PopUpMainframe
236 |  | MILESTONE IMS General Setup Completed
237 |  | MILESTONE IMS General Completed
238 | 8.4.2 | IMS (Database-{1,2....n} ) For each Database, Repeat the below |  | in conjuncton with IMS Application but could be stand-alone if DB's only referenced by CICS for example
239 | 8.4.2.1 | Setup
240 | 8.4.2.1.1 | Identify required databases |  | Application Team
241 | 8.4.2.1.2 | Determine migration method (db datasets/restore IC) |  | PopUpMainframe
242 | 8.4.2.1.3 | Calculate PopUp DASD requirements and ensure sufficient space is available |  | PopUpMainframe
243 | 8.4.2.1.4 | Identify Buffer Pools etc required for PopUp "clone" |  | PopUpMainframe
244 |  | MILESTONE IMS Database Setup Completed
245 | 8.4.2.2 | Preparation
246 | 8.4.2.2.1 | Identify:
247 | 8.4.2.2.1.1 | Database Datasets |  | Application Team
248 | 8.4.2.2.1.2 | RECON records |  | Application Team
249 |  | MILESTONE IMS Database Preparation Completed
250 | 8.4.2.3 | Corral Data
251 | 8.4.2.3.1 | Transfer database datasets/IC |  | PopUpMainframe
252 |  | MILESTONE IMS Database Corral Data Completed
253 | 8.4.2.4 | DeCorral
254 | 8.4.2.4.1 | Restore/Create databases |  | PopUpMainframe
255 | 8.4.2.4.2 | Confirm all data transferred successfully (record counts?) |  | PopUpMainframe
256 |  | MILESTONE IMS Database DeCorral Data Completed
257 | 8.4.2.5 | Post-Decorral
258 | 8.4.2.5.1 | Confirm all data transferred successfully
259 | 8.4.2.5.2 | Modify JCL to suit PopUp environment |  | PopUpMainframe
260 | 8.4.2.5.3 | Customise Buffer Pools on PopUp |  | PopUpMainframe
261 | 8.4.2.5.4 | Create required databases on PopUp (RECON update) |  | PopUpMainframe
262 |  | MILESTONE IMS Database Post DeCorral Completed
263 | 8.4.2.6 | Smoke Test
264 | 8.4.2.6.1 | Execute DDLTO against db
265 | 8.4.2.6.2 | Execute designated application program to confirm operability
266 |  | MILESTONE IMS Database Smoke Test Completed
267 |  | MILESTONE IMS Database Completed (per Database)
268 | 8.4.3 | IMS (Application- {1,2....n} ) For each Application , Repeat the below
269 | 8.4.3.1 | Setup
270 | 8.4.3.1.1 | Identify application specific libraries (DBDLIB/PSBLIB) |  | Application Team
271 |  | MILESTONE IMS Appl Setup Completed
272 | 8.4.3.2 | Preparation
273 | 8.4.3.2.1 | Identify Correct Release of:
274 | 8.4.3.2.1.1 | Execution JCL/PROCLIBs |  | Application Team
275 | 8.4.3.2.1.2 | EXECutable code |  | Application Team
276 |  | MILESTONE IMS Appl Preparation Completed
277 | 8.4.3.3 | Corral Data
278 | 8.4.3.3.1 | Transfer application specific IMS libraries |  | PopUpMainframe
279 |  | MILESTONE IMS Appl Corral Data Completed
280 | 8.4.3.4 | DeCorral
281 | 8.4.3.4.1 | Restore application libraries |  | PopUpMainframe
282 |  | MILESTONE IMS Appl DeCorral Data Completed
283 | 8.4.3.5 | Post-Decorral
284 | 8.4.3.5.1 | Confirm all data transferred successfully
285 | 8.4.3.5.2 | Modify JCL to suit PopUp environment
286 |  | MILESTONE IMS Appl Post DeCorral Completed
287 | 8.4.3.6 | Smoke Test
288 | 8.4.3.6.1 | Execute designated application program to confirm operability
289 |  | MILESTONE IMS Appl Smoke Test Completed
290 |  | MILESTONE IMS Appl Completed (per Database)
291 |  | MILESTONE IMS Completed (for all Databases & all Applications)
292 | 8.5 | MQ
293 | 8.5.1 | MQ (General)
294 | 8.5.1.1 | Setup
295 | 8.5.1.1.1 | Ensure correct release of MQ is installed |  | PopUpMainframe
296 | 8.5.1.1.2 | Identify external connections and listener ports required |  | PopUpMainframe
297 | 8.5.1.1.3 | Identify messaging architecture (cluster/point-to-point/pub-sub etc) |  | PopUpMainframe
298 | 8.5.1.1.4 | Identify additional requirements (exits etc) |  | PopUpMainframe
299 | 8.5.1.1.5 | Identify and configure connected mainframe systems (IMS/CICS Bridge etc) |  | PopUpMainframe
300 |  | MILESTONE MQ General Setup Completed
301 |  | MILESTONE MQ General Completed
302 | 8.5.2 | MQ (Application {1,2....n} ) For each Application, Repeat the below
303 | 8.5.2.1 | Setup
304 | 8.5.2.1.1 | Identify application specific objects (queues/channels) |  | PopUpMainframe
305 | 8.5.2.1.2 | Confirm no queue data is required in PopUp (additional work required if needed) |  | PopUpMainframe
306 | 8.5.2.1.3 | Identify application libraries/datasets |  | PopUpMainframe
307 |  | MILESTONE MQ Appl Setup Completed
308 | 8.5.2.2 | Preparation
309 | 8.5.2.2.1 | Copy required objects from target system (CSQUTIL SDEFS or MAKEDEF) |  | PopUpMainframe
310 | 8.5.2.2.2 | Copy required application libraries/datasets |  | PopUpMainframe
311 | 8.5.2.2.3 | Agree transfer method(s) ( Migration Utility / FTP / etc ) |  | PopUpMainframe&Application Team
312 |  | MILESTONE MQ Appl Preparation Completed
313 | 8.5.2.3 | Corral Data
314 | 8.5.2.3.1 | Transfer Definitions to PopUp |  | PopUpMainframe
315 |  | MILESTONE MQ Appl Corral Data Completed
316 | 8.5.2.4 | DeCorral (PopUp)
317 | 8.5.2.4.1 | Decorral MQ objects |  | PopUpMainframe
318 | 8.5.2.4.2 | Confirm all data transferred successfully (use queue/channel counts) |  | PopUpMainframe
319 |  | MILESTONE MQ Appl Decorral Data Completed
320 | 8.5.2.5 | Post-Decorral
321 | 8.5.2.5.1 | Copy required application libraries/datasets |  | PopUpMainframe
322 | 8.5.2.5.2 | Modify JCL to suit PopUp environment |  | PopUpMainframe
323 | 8.5.2.5.3 | Customise objects (may need to customise channel connection parms etc) |  | PopUpMainframe
324 | 8.5.2.5.4 | Run CSQUTIL to create objects on PopUp Qmanager |  | PopUpMainframe
325 | 8.5.2.5.5 | Confirm all objects created successfully (check RC; use queue/channel counts) |  | PopUpMainframe
326 | 8.5.2.5.6 | Display queues, channels etc (CSQUTIL or MQ panels) |  | PopUpMainframe
327 |  | MILESTONE MQ Appl Post Decorral Completed
328 | 8.5.2.6 | Smoke Test
329 | 8.5.2.6.1 | Execute designated application program to confirm operability |  | PopUpMainframe&Application Team
330 |  | MILESTONE MQ Appl Smoke Test Completed
331 |  | MILESTONE MQ Appl Completed (per Application)
332 |  | MILESTONE MQ Completed (for all Applications)
333 | 8.6 | External Tool / Utility-{1,2....n}
334 | 8.6.1 | Setup
335 | 8.6.1.1 | Discover pre-requisites |  | PopUpMainframe
336 | 8.6.1.2 | Raise request for license (for any 3rd party tools) |  | PopUpMainframe
337 | 8.6.1.3 | Acquire all the required documentation and any other artifacts |  | PopUpMainframe
338 | 8.6.1.4 | Install Tool |  | PopUpMainframe
339 | 8.6.1.5 | Configure Tool |  | PopUpMainframe
340 |  | MILESTONE Extenal Tool/Utility Setup Completed
341 | 8.6.2 | Smoke Test
342 | 8.6.2.1 | Execute designated application program to confirm operability |  | Application Team
343 |  | MILESTONE Smoke Test Completed
344 |  | MILESTONE External Tool/utility completed ( per tool/utility)
345 |  | MILESTONE External Tool/utility completed ( All of the tools/utilities )
346 | 9 | PopUp Virtualisation - PopUp target 1 with <Application> |  |  | NOT STARTED
347 | 9.1 | Check PopUp readiness for Data Ingestion ( all in scope application and data are available) & shutdown PopUp |  | PopUpMFDeveloper
348 | 9.2 | Check Delphix Virtualization Engine Readiness for Data Ingestion : Start / Stop Server |  | PopUpMFDeveloper
349 | 9.3 | Create Environment in Delphix |  | PopUpMFDeveloper
350 | 9.4 | Ingest PopUp into Delphix Virtualization & create “Gold Copy" (Based on Network speed effort will vary) |  | PopUpMFDeveloper
351 | 9.5 | Provision PopUp targets (Virtual PopUps) |  | PopUpMFDeveloper
352 | 9.6 | Shake down testing on All subsystems ( CICS / Db2 / IMS etc ) on Virtual PopUps |  | PopUpMFDeveloper
353 | 9.7 | Review Virtual PopUp and Signoff |  | Client
354 |  | MILESTONE PopUp Virtualization completed (1 Virtual PopUp mainframe)
355 |  | MILESTONE PopUp Virtualization completed (All of the Virtual PopUp mainframe)
356 | 10 | Adhoc Tasks |  |  | NOT STARTED
357 | 10.1 | Volume creation ( Per Volume -0.5) |  | PopUpLINUXLead
358 |  | MILESTONE Adhoc Tasks completed
359 | 11 | Documentation & Instructions for PopUp including : |  |  | NOT STARTED
360 | 11.1 | List of All of the Mainframe objects transferred per Application to PopUp |  | PopUpMFDeveloper
361 | 11.2 | Frequently requried tasks on PopUp
362 | 11.2.1 | New User ID creation |  | PopUpMFDeveloper
363 | 11.2.2 | New Volume creation |  | PopUpMFDeveloper
364 | 11.2.3 | Lessons Learned document |  | PopUpMFDeveloper
365 |  | MILESTONE Documentation & Instructions - Frequent tasks on PopUP completed
366 |  | MILESTONE Documentation & Instructions for PopUp completed
Note on C179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: dependent on number of datasets
Note on C184: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: dependent on number of datasets
Note on C187: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: dependent on number of datasets
Note on C359: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: dependent on number of Volumes

## Setup & Prep Checklist
Setup & Preparation Checklist
No | Delivery Manual Stage | Activity / Document (must be signed off) | Status | Sign Off Provided by | Sign Off Date
1 | A1. Project Definition & Kickoff | Project Charter
2 | A2. Architecture & Application Discovery | List of applications in scope for project
3 | A2. Architecture & Application Discovery | Full infrastructure blueprint (logical architecture, network architecture, VM requirements, z/OS software)
4 | A2. Architecture & Application Discovery | Network requirements for in-scope applications
5 | A2. Architecture & Application Discovery | Data migration strategy (e.g. Connect:Direct or Migration Server)
6 | A2. Architecture & Application Discovery | Application Discovery Document which includes list of data and application components to be virtualised (including sizing details)
7 | A2. Architecture & Application Discovery | List of data field types to be masked (if applicable)
8 | A3. Popup & Delphix Infrastructure Setup | PopUp appliances created as per infrastructure blueprint
9 | A3. Popup & Delphix Infrastructure Setup | PopUp appliances health check completed successfully
10 | A3. Popup & Delphix Infrastructure Setup | Delphix Continuous Data Engine appliances created as per infrastructure blueprint
11 | A3. Popup & Delphix Infrastructure Setup | Delphix Continuous Compliance Engine appliances created as per infrastructure blueprint
12 | A3. Popup & Delphix Infrastructure Setup | Delphix Continuous Data Engine appliances appliances health check completed successfully
13 | A3. Popup & Delphix Infrastructure Setup | Delphix Continuous Compliance Engine appliances appliances health check completed successfully
14 | A3. Popup & Delphix Infrastructure Setup | User access (for project team) to PopUp & Delphix appliances validated
15 | A4. Data Migration Preparation | Migration Server utility installed and configured
16 | A4. Data Migration Preparation | Migration Server security configured and tested
17 | A4. Data Migration Preparation | Transport volumes created
18 | A4. Data Migration Preparation | All data in scope for virtualisation copied to transport volume Note: data must be consistent i.e. time snapshot
19 | A4. Data Migration Preparation | Migration Server utility up and running

## ChangeHistory
Version No | Date | Description of changes | Changes done by
0.01 |  | Initial Template
0.02 | 2025-10-01 | Change to fix spelling and logo | Stuart/Muthiah

## Assumptions
Estimation here is based on the below assumptions/criteria. The estimation can be expanded based on the number of applications as well as the size of data.
| 1 | Table with 100,000 rows max
| 2 | 1 VSAM file of size ?
| 3 | No NETWORK slowness issue
| 4 | Medium Complexity over Data & Data transfer
| 5 | Not considering unknown complexity
To arrive at an approx estimation on the below, as it was done for Db2 & VSAM
CICS
IMS
MQ